## Sheet1
環境​ | 環境 | 今後の方針 | 認証設定 | 登録ﾎｽﾄ名 | 所属ﾄﾞﾒｲﾝ名 | LB_IPｱﾄﾞﾚｽ | LB名 | IF | 環境 | 種別​ | ホスト名​ | IPアドレス | 稼働ステータス​ | LB機器情報 | BIG-IP登録LB名 | apa-tom停止 | 負荷分散 切り離し時刻 | ProcessMonitor 修正時刻 | apa-tom 停止時刻 | 起動スクリプト リネーム時刻 | 全行程 完了時刻
本番 | 本番社内1面 | 2024/3 利用終了 | 社内認証 | delivery | bc-extra.net | 192.168.215.51 | thap101x | p1 | s01 | AP​ | thap101v |  | 稼働​ | BIG-IP(192.168.237.183) |  | 要
本番 | 本番社内1面 | 2024/3 利用終了 | 社内認証 | delivery | bc-extra.net | 192.168.215.53 | thap101x | p1 | s01 | AP​ | thap102v |  | 稼働​ | BIG-IP(192.168.237.183) |  | 要
本番 | 本番社内1面 | 2024/3 利用終了 | 社内認証 | delivery | bc-extra.net | 192.168.215.54 | thap101x | p1 | s01 | AP​ | thap103v |  | 稼働​ | BIG-IP(192.168.237.183) |  | 要
本番 | - | - | - | - | - | - | - | - | - | - | thap104v | - | 撤去 | - | - | 不要 | - | - | - | - | -
本番 | - | - | - | - | - | - | - | - | - | - | thap105v | - | 撤去 | - | - | 不要 | - | - | - | - | -
本番 | - | - | - | - | - | - | - | - | - | - | thap106v | - | 撤去 | - | - | 不要 | - | - | - | - | -
本番 | 本番社内2面 | 2024/3 利用終了 | 社内認証 | delivery-staging | bc-extra.net | 192.168.215.141 | thap111x | p1 | s01 | AP​ | thap111v |  | 稼働​ |  |  | 要
本番 | 社内CO後負荷テスト環境 | 2024/3 利用終了 | 社内認証 | delivery-staging2 | bc-extra.net | 192.168.215.23 | thap121x | p1 | s01 | AP​ | thap121v |  | 稼働​ |  |  | 要
検証 | 検証社内1面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t1 | bc-extra.net | 172.21.96.120 | thap501x | p1 | s01 | AP​ | thap501v | 172.21.96.121 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap501x.bc-extra.net_0 | 要
検証 | 検証社内1面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t1 | bc-extra.net | 172.21.96.120 | thap501x | p1 | s01 | AP​ | thap502v | 172.21.96.122 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap501x.bc-extra.net_0 | 実機確認⇒要
検証 | 検証社内1面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | [7 empty] | BAT​ | thbt501v |  | 稼働​ |  |  | 実機確認⇒不要
検証 | 検証社内1面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb501v |  | 稼働​ |  |  | 不要
検証 | 検証社内1面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb502v |  | 稼働​ |  |  | 不要
検証 | - | - | - | - | - | - | - | - | - | - | thap531v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | 検証社内1面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t1 | bc-extra.net | 172.21.161.0 | thfr551x | p1 | s01 | WEB​ | thfr551v | 172.21.161.1 | 稼働​ | BIG-IP® (192.168.59.4) | thfr551x_vip-80 | 要
検証 | 検証社内2面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t1-staging | bc-extra.net | 172.21.96.128 | thap511x | p1 | s01 | AP​ | thap511v | 172.21.96.129 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap511x.bc-extra.net_0 | 要
検証 | - | - | - | - | - | - | - | - | - | - | thap546v | - | 撤去 | - | - | 不要 | - | - | - | - | -
本番 | 本番社内1面 | 2024/3 利用終了 | [7 empty] | BAT​ | thbt101v |  | 稼働​ |  |  | 不要
本番 | 社内CO後負荷テスト環境 | 2024/3 利用終了 | [7 empty] | BAT​ | thbt121v |  | 稼働​ |  |  | 不要
検証 | 検証社内2面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb511v |  | 稼働​ |  |  | 不要
検証 | 検証社内2面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t1-staging | bc-extra.net | 172.21.161.2 | thfr561x | p1 | s01 | WEB​ | thfr561v | 172.21.161.3 | 稼働​ | BIG-IP® (192.168.59.4) | thfr561x_vip-80 | 要
検証 | 検証社内3面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t2 | bc-extra.net | 172.21.96.132 | thap521x | p1 | s01 | AP​ | thap521v | 172.21.96.134 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap521x.bc-extra.net_0 | 要
本番 | 本番社内1面 | 2024/3 利用終了 | [7 empty] | DB​ | thdb101v |  | 稼働​ |  |  | 不要
本番 | 本番社内1面 | 2024/3 利用終了 | [7 empty] | DB​ | thdb102v |  | 稼働​ |  |  | 不要
本番 | 本番社内1面 | 2024/3 利用終了 | [7 empty] | DB​ | thdb103v |  | 稼働​ |  |  | 不要
本番 | 本番社内2面 | 2024/3 利用終了 | [7 empty] | DB​ | thdb111v |  | 稼働​ |  |  | 不要
本番 | 社内CO後負荷テスト環境 | 2024/3 利用終了 | [7 empty] | DB​ | thdb121v |  | 稼働​ |  |  | 不要
検証 | 検証社内3面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t2-staging | bc-extra.net | 172.21.96.133 | thap531x | p1 | s02 | AP​ | thap521v | 172.21.96.135 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap531x.bc-extra.net_0 | 要
検証 | 検証社内3面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | BAT​ | thbt521v |  | 稼働​ |  |  | 不要
検証 | 検証社内3面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb521v |  | 稼働​ |  |  | 不要
検証 | 検証社内3面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb522v |  | 稼働​ |  |  | 不要
検証 | 検証社内3面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t2 | bc-extra.net | 172.21.161.4 | thfr571x | p1 | s01 | WEB​ | thfr571v | 172.21.161.6 | 稼働​ | BIG-IP® (192.168.59.4) | thfr571x_vip-80 | 要
検証 | 検証社内3面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t2-staging | bc-extra.net | 172.21.161.5 | thfr581x | p1 | s02 | WEB​ | thfr571v | 172.21.161.7 | 稼働​ | BIG-IP® (192.168.59.4) | thfr581x_vip-80 | 要
検証 | - | - | - | - | - | - | - | - | - | - | thdb546v | - | 撤去 | - | - | 不要 | - | - | - | - | -
本番 | 本番社内1面 | 2024/3 利用終了 | 社内認証 | deli | bc-extra.net | 172.24.15.139 | thfr151x | p1 | s01 | WEB​ | thfr151v |  | 稼働​ |  |  | 要
本番 | 本番社内2面 | 2024/3 利用終了 | 社内認証 | deli-staging | bc-extra.net | 172.24.15.140 | thfr161x | p1 | s01 | WEB​ | thfr161v |  | 稼働​ |  |  | 要
本番 | 社内CO後負荷テスト環境 | 2024/3 利用終了 | 社内認証 | deli-staging2 | bc-extra.net | 172.24.15.184 | thfr171x | p1 | s01 | WEB​ | thfr171v |  | 稼働​ |  |  | 要
検証 | - | - | - | - | - | - | - | - | - | - | thfr501v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | - | - | - | - | - | - | - | - | - | - | thfr502v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | - | - | - | - | - | - | - | - | - | - | thfr511v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | - | - | - | - | - | - | - | - | - | - | thfr521v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | - | - | - | - | - | - | - | - | - | - | thfr531v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | 検証社内5面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t3 | bc-extra.net | 172.21.96.141 | thap541x | p1 | s01 | AP​ | thap541v | 172.21.96.143 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap541x.bc-extra.net_0 | 要
検証 | 検証社内5面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t3-staging | bc-extra.net | 172.21.96.142 | thap546x | p1 | s02 | AP​ | thap541v | 172.21.96.144 | 稼働​ | BIG-IP® (192.168.237.183) | LB80-thap546x.bc-extra.net_0 | 要
検証 | 検証社内5面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | BAT​ | thbt541v |  | 稼働​ |  |  | 不要
検証 | 検証社内5面 | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb541v |  | 稼働​ |  |  | 不要
検証 | - | - | - | - | - | - | - | - | - | - | thfr581v | - | 撤去 | - | - | 不要 | - | - | - | - | -
検証 | 検証社内5面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t3 | bc-extra.net | 172.21.161.8 | thfr591x | p1 | s01 | WEB​ | thfr591v | 172.21.161.10 | 稼働​ | BIG-IP® (192.168.59.4) | thfr591x_vip-80 | 実機確認⇒要
検証 | 検証社内5面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t3-staging | bc-extra.net | 172.21.161.9 | thfr596x | p1 | s02 | WEB​ | thfr591v | 172.21.161.11 | 稼働​ | BIG-IP® (192.168.59.4) | thfr596x_vip-80 | 実機確認⇒要
検証 | - | - | - | - | - | - | - | - | - | - | thfr596v | - | 撤去 | - | - | 不要 | - | - | - | - | -

## 元データ
↓ 2024/3/26時点
| 環境​ | 環境 | 今後の方針 | 認証設定 | 登録ﾎｽﾄ名 | 所属ﾄﾞﾒｲﾝ名 | IPｱﾄﾞﾚｽ | LB名 | IF | 環境 | 種別​ | ホスト名​ | 稼働ステータス​
| 本番1面​ | 本番社内1面 | 2024/3 利用終了 | 社内認証 | deli | bc-extra.net | 172.24.15.139 | thfr151x | p1 | s01 | WEB​ | thfr151v | 稼働​
|  |  | 2024/3 利用終了 | 社内認証 | delivery | bc-extra.net | 192.168.215.51 | thap101x | p1 | s01 | AP​ | thap101v | 稼働​
[7 empty] | 192.168.215.53 |  |  | s01 |  | thap102v | 稼働​
[7 empty] | 192.168.215.54 |  |  | s01 |  | thap103v | 稼働​
|  |  | 2024/3 利用終了 | [7 empty] | BAT​ | thbt101v | 稼働​
|  |  | 2024/3 利用終了 | [7 empty] | DB​ | thdb101v | 稼働​
[12 empty] | thdb102v | 稼働​
[12 empty] | thdb103v | 稼働​
| 本番2面​ | 本番社内2面 | 2024/3 利用終了 | 社内認証 | deli-staging | bc-extra.net | 172.24.15.140 | thfr161x | p1 | s01 | WEB​ | thfr161v | 稼働​
|  |  | 2024/3 利用終了 | 社内認証 | delivery-staging | bc-extra.net | 192.168.215.141 | thap111x | p1 | s01 | AP​ | thap111v | 稼働​
|  |  | 2024/3 利用終了 | [7 empty] | DB​ | thdb111v | 稼働​
| 本番3面​ | 社内CO後負荷テスト環境 | 2024/3 利用終了 | 社内認証 | deli-staging2 | bc-extra.net | 172.24.15.184 | thfr171x | p1 | s01 | WEB​ | thfr171v | 稼働​
|  |  | 2024/3 利用終了 | 社内認証 | delivery-staging2 | bc-extra.net | 192.168.215.23 | thap121x | p1 | s01 | AP​ | thap121v | 稼働​
|  |  | 2024/3 利用終了 | [7 empty] | BAT​ | thbt121v | 稼働​
|  |  | 2024/3 利用終了 | [7 empty] | DB​ | thdb121v | 稼働​
| 検証1面​ | 検証社内1面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t1 | bc-extra.net | 172.21.161.0 | thfr551x | p1 | s01 | WEB​ | thfr551v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t1 | bc-extra.net | 172.21.96.120 | thap501x | p1 | s01 | AP​ | thap501v | 稼働​
[7 empty] | 172.21.96.122 |  |  | s01 |  | thap502v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | [7 empty] | BAT​ | thbt501v | 稼働​
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb501v | 稼働​
[12 empty] | thdb502v | 稼働​
| 検証2面​ | 検証社内2面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t1-staging | bc-extra.net | 172.21.161.2 | thfr561x | p1 | s01 | WEB​ | thfr561v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t1-staging | bc-extra.net | 172.21.96.128 | thap511x | p1 | s01 | AP​ | thap511v | 稼働​
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb511v | 稼働​
| 検証3面​ | 検証社内3面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t2 | bc-extra.net | 172.21.161.4 | thfr571x | p1 | s01 | WEB​ | thfr571v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t2-staging | bc-extra.net | 172.21.161.7 |  |  | s02 |  |  |  | ↓1
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t2 | bc-extra.net | 172.21.96.130 | thdb511x | p1 | s01 | AP​ | thap521v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t2-staging | bc-extra.net | 172.21.96.135 |  |  | s02 |  |  |  | ↓2
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | BAT​ | thbt521v | 稼働​
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb521v | 稼働​
[12 empty] | thdb522v | 稼働​
| 検証5面​ | 検証社内5面 | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t3 | bc-extra.net | 172.21.161.8 | thfr591x | p1 | s01 | WEB​ | thfr591v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | deli-t3-staging | bc-extra.net | 172.21.161.11 |  |  | s02 |  |  |  | ↓3
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t3 | bc-extra.net | 172.21.96.141 | thap541x | p1 | s01 | AP​ | thap541v | 稼働​
|  |  | 2024/3 利用終了・4/3 apa+tom停止・4/11 OS停止予定 | 社内認証 | delivery-t3-staging | bc-extra.net | 172.21.96.144 |  |  | s02 |  |  |  | ↓4
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | BAT​ | thbt541v | 稼働​
|  |  | 2024/3 利用終了・4/11 OS停止予定 | [7 empty] | DB​ | thdb541v | 稼働​
撤去済み環境
| 環境​ | 環境 |  |  | 登録ﾎｽﾄ名 | 所属ﾄﾞﾒｲﾝ名 | IPｱﾄﾞﾚｽ | LB名 | IF |  | 種別​ | ホスト名​ | 稼働ステータス​
[12 empty] | thap104v | 撤去
[12 empty] | thap105v | 撤去
[12 empty] | thap106v | 撤去
[12 empty] | thfr501v | 撤去
[12 empty] | thfr502v | 撤去
[12 empty] | thfr511v | 撤去
[12 empty] | thfr521v | 撤去
[12 empty] | thfr531v | 撤去
|  | 検証社内3面 |  |  | deli-t2-staging | bc-extra.net | 172.21.161.5 | thfr581x | p1 |  |  | thfr581v | 撤去 | ↑1..
|  | 検証社外3面 |  |  | delivery-t2-staging | bc-extra.net | 172.21.96.132 | thap521x | p1 |  |  | thap531v | 撤去 | ↑2..
|  | 検証社内5面 |  |  | deli-t3-staging | bc-extra.net | 172.21.161.9 | thfr596x | p1 |  |  | thfr596v | 撤去 | ↑3..
|  | 検証社外5面 |  |  | delivery-t3-staging | bc-extra.net | 172.21.96.142 | thap546x | p1 |  |  | thap546v | 撤去 | ↑4..
[12 empty] | thdb546v | 撤去

## export-2024-03-29-15-57-43
Short Hostname | Linux ps -efwww ¦grep[http] | Count
thap101v | root 26454 1 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26467 26454 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26468 26454 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26469 26454 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26470 26454 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26471 26454 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap102v | root 9871 1 0 04:01 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9883 9871 0 04:01 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9884 9871 0 04:01 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9885 9871 0 04:01 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9886 9871 0 04:01 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9887 9871 0 04:01 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 24651 9871 0 05:31 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap103v | apache 13693 13761 0 11:46 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 13761 1 0 04:03 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13773 13761 0 04:03 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13774 13761 0 04:03 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13775 13761 0 04:03 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13776 13761 0 04:03 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13777 13761 0 04:03 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap111v | apache 10613 27953 0 07:05 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 27953 1 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27965 27953 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27966 27953 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27967 27953 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27968 27953 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27969 27953 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap121v | apache 7528 14916 0 04:46 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 14916 1 0 04:00 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14931 14916 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14932 14916 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14933 14916 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14934 14916 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14935 14916 0 04:00 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap501v | root 4290 1 0 2021 ? 00:38:02 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7977 4290 0 06:05 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9794 4290 0 10:34 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 16908 4290 0 10:22 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 17156 4290 0 15:29 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 19719 4290 0 07:38 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26358 4290 0 06:28 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap502v | [root@thap502v ~]# ps -efwww ¦ grep "http" ¦ grep "/apache/conf/httpd.conf" root 2006 1 0 2023 ? 00:15:13 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 3329 2006 0 08:29 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10171 2006 0 08:32 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 11509 2006 0 10:40 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 17759 2006 0 15:35 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 18870 18298 0 16:04 pts/0 00:00:00 grep /apache/conf/httpd.conf apache 26773 2006 0 09:34 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 30581 2006 0 01:37 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf [root@thap502v ~]#
thap511v | apache 1941 21210 0 03:41 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 19554 21210 0 05:29 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 20720 21210 0 10:25 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 21210 1 0 2019 ? 01:21:16 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 32135 21210 0 08:48 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 32175 21210 0 14:55 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thap521v | apache 1274 2062 0 06:55 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf root 2027 1 0 2023 ? 00:05:35 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 2062 1 0 2023 ? 00:05:42 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 6459 2027 0 00:50 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14199 2062 0 14:29 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 16032 2027 0 10:47 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 22729 2027 0 15:25 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 23031 2062 0 01:36 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 24782 2062 0 02:03 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 26873 2062 0 08:24 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 27283 2027 0 11:31 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 28024 2027 0 03:36 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 29406 2062 0 11:45 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf | 1
thap541v | root 2013 1 0 2023 ? 00:05:32 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 2043 1 0 2023 ? 00:05:37 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 11526 2043 0 06:12 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 11541 2043 0 06:12 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 11622 2043 0 06:12 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 16141 2043 0 06:17 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 17091 2013 0 03:24 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 18184 2013 0 03:25 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 19703 2043 0 06:21 ? 00:00:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 20888 2013 0 03:28 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 22697 2013 0 03:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 24400 2013 0 03:32 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thbt101v | [no results] | 1
thbt121v | [no results] | 1
thbt501v | [no results] | 1
thbt521v | [no results] | 1
thbt541v | [no results] | 1
thdb101v | [no results] | 1
thdb102v | [no results] | 1
thdb103v | [no results] | 1
thdb111v | [no results] | 1
thdb121v | [no results] | 1
thdb501v | [no results] | 1
thdb502v | [no results] | 1
thdb511v | [no results] | 1
thdb521v | [no results] | 1
thdb522v | [no results] | 1
thdb541v | [no results] | 1
thfr151v | apache 15593 31172 0 14:54 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 31172 1 0 04:30 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 31197 31172 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 31198 31172 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 31199 31172 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 31200 31172 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 31201 31172 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thfr161v | root 7698 1 0 04:30 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7710 7698 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7711 7698 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7712 7698 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7713 7698 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 7714 7698 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thfr171v | apache 3798 10888 0 06:47 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 10888 1 0 04:30 ? 00:00:01 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10900 10888 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10901 10888 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10902 10888 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10903 10888 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10904 10888 0 04:30 ? 00:00:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thfr551v | root 1921 1 0 2018 ? 01:27:54 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 3483 1921 0 2022 ? 00:04:18 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 10372 1921 0 2021 ? 00:07:30 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14772 1921 0 2021 ? 00:07:29 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 16784 1921 0 2023 ? 00:00:55 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 20343 1921 0 2022 ? 00:05:20 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 20624 1921 0 2022 ? 00:04:15 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 21173 1921 0 2021 ? 00:07:29 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 21360 1921 0 2022 ? 00:04:13 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27990 1921 0 2021 ? 00:08:27 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 29603 1921 0 2021 ? 00:07:40 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thfr561v | root 1984 1 0 2023 ? 00:06:00 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1994 1984 0 2023 ? 00:02:09 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1995 1984 0 2023 ? 00:02:09 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1996 1984 0 2023 ? 00:02:09 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1997 1984 0 2023 ? 00:02:10 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1998 1984 0 2023 ? 00:02:08 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 24448 1984 0 2023 ? 00:02:12 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf | 1
thfr571v | apache 338 15238 0 2021 ? 00:09:32 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 432 15238 0 2023 ? 00:04:01 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 1083 29449 0 2022 ? 00:04:52 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 4179 29449 0 2022 ? 00:04:53 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9673 15238 0 2022 ? 00:06:30 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 9858 29449 0 2023 ? 00:04:05 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 13161 15238 0 2023 ? 00:04:39 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf root 15238 1 0 2019 ? 01:33:44 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 15270 15238 0 2023 ? 00:04:10 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 16203 29449 0 2021 ? 00:11:53 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 17327 15238 0 2022 ? 00:05:20 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 17328 29449 0 2022 ? 00:04:52 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 21156 29449 0 2023 ? 00:04:08 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 21666 15238 0 2021 ? 00:09:28 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 22990 29449 0 2022 ? 00:06:29 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 25571 15238 0 2023 ? 00:04:39 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 25747 15238 0 2023 ? 00:04:00 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 26633 29449 0 2022 ? 00:04:57 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26634 29449 0 2022 ? 00:04:55 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 27929 29449 0 2023 ? 00:03:49 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 29449 1 0 2019 ? 01:32:39 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 32592 15238 0 2022 ? 00:05:14 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf | 1
thfr591v | [root@thfr591v ~]# ps -efwww ¦ grep "http" ¦ grep "/apache/conf/httpd.conf" root 1972 1 0 2018 ? 01:14:27 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1980 1972 0 2018 ? 00:16:12 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 1981 1972 0 2018 ? 00:16:13 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 2013 1 0 2018 ? 01:12:34 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 2019 2013 0 2018 ? 00:26:43 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 2020 2013 0 2018 ? 00:26:37 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 2021 2013 0 2018 ? 00:26:38 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 2022 2013 0 2018 ? 00:26:33 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 2023 2013 0 2018 ? 00:26:27 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 6904 1972 0 2020 ? 00:12:26 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf root 7045 6886 0 16:06 pts/0 00:00:00 grep /apache/conf/httpd.conf apache 9802 1972 0 2018 ? 00:15:18 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9819 1972 0 2018 ? 00:15:20 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9826 1972 0 2018 ? 00:15:15 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 9827 1972 0 2018 ? 00:15:18 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 14255 1972 0 2020 ? 00:10:17 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 24388 1972 0 2020 ? 00:12:23 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 26831 1972 0 2020 ? 00:12:28 /opt/s01/apache/bin/httpd -f /opt/s01/apache/conf/httpd.conf apache 29711 2013 0 2018 ? 00:26:25 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf apache 29997 2013 0 2018 ? 00:27:02 /opt/s02/apache/bin/httpd -f /opt/s02/apache/conf/httpd.conf [root@thfr591v ~]#